## Implementation Plan & Estimate
Task Name | Description | Duration (Hours) | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5
Project Setup & SDD Initialization | Initialize the GitHub repository and establish the unified spec.md. Setup the FastAPI and React project environments. | 1 | █ | █
Database & Architecture Design | Finalize system components, data flow, and database schema mappings. Set up local development containers. | 1.5 |  |  | █ | █ | █
Backend API Development | Develop python backend and Implement FastAPI with endpoints to handle route search requests. | 5 | [5 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Create Mock Data to simulate SAFER API | Build mock data structures for requested city pairs. | 1.5 | [15 empty] | █ | █ | █
Frontend Web Portal | Build the React UI with city input fields and search trigger. Integrate Google Maps embed. Connect to backend API. | 4 | [18 empty] | █ | █ | █ | █ | █ | █ | █ | █
Deployment & Pipeline Configuration | Configure the repository for a Heroku deployment by adding a Procfile and configuring FastAPI to serve the compiled React frontend as static files. Connect the GitHub repository to a Heroku app, assign the Node.js and Python buildpacks, and trigger an automated deployment to generate a live, public URL. | 2 | [26 empty] | █ | █ | █ | █
Documentation & Final Review | Create the README and provide licensing information. | 0.5 | [30 empty] | █

## Coding Standards
Concept / Data Type | Python Standard (PEP 8) | Database Standard (SQL) | GenLogs Examples
Standard Variables / Columns | snake_case | snake_case (Singular) | dot_number, carrier_score, origin_city
Data Models / Tables | PascalCase | snake_case (Plural) | Python: CarrierProfile DB: carrier_profiles
Primary Keys | Usually id property | id | id
Foreign Keys | [table]_id | [table]_id (Singular table name) | carrier_id, lane_id
Booleans | is_, has_, can_ prefix | is_, has_, can_ prefix | is_inbound, has_hazmat
Dates / Timestamps | _at or _date suffix | _at or _date suffix | detected_at, authorized_date
Counts / Totals | _count or _total suffix | _count or _total suffix | fleet_size_min, observation_count
Raw Data / JSON | _data or _payload suffix | _data or _payload suffix | real_time_locs, fmcsa_data
Functions / Methods | snake_case | N/A | fetch_carrier_recommendations(), calculate_lane_score()
Constants | UPPER_SNAKE_CASE | N/A | MAX_SEARCH_RADIUS, DEFAULT_CARRIER_SCORE
Private / Internal Variables | _snake_case (Leading underscore) | N/A | _api_token, _cached_detections
Database Indexes | N/A | [table]_[column]_idx | carriers_dot_number_idx
Database Constraints | N/A | [table]_[column]_[type] | carriers_dot_number_unq

## Database
1. CARRIER Table
Purpose: Stores motor carrier company data enriched by the SAFER FMCSA API.
Column Name | Data Type | Constraints | Description
id | UUID | PRIMARY KEY | Unique internal identifier.
dot_number | VARCHAR(255) | UNIQUE, NOT NULL | The USDOT number used for external lookups.
name | VARCHAR(255) | NOT NULL | Legal name of the carrier company.
mc_number | VARCHAR(255) | - | Motor Carrier identifier (if applicable).
last_fmcsa_sync | TIMESTAMP | - | Timestamp of the last update from the SAFER API.
2. VEHICLE Table
Purpose: Stores individual physical assets (trucks) associated with a specific carrier.
Column Name | Data Type | Constraints | Description
id | UUID | PRIMARY KEY | Unique internal identifier.
carrier_id | UUID | FOREIGN KEY | Links to CARRIER.id.
vin | VARCHAR(17) | UNIQUE, NOT NULL | Vehicle Identification Number.
license_plate | VARCHAR(20) | - | The alphanumeric code on the plate.
plate_state | VARCHAR(2) | - | US state code of the plate issue.
3. SIGHTING Table
Purpose: A high-volume log of every truck capture processed by the trident Sensors.
Column Name | Data Type | Constraints | Description
id | UUID | PRIMARY KEY | Unique internal identifier.
vehicle_id | UUID | FOREIGN KEY | Links to VEHICLE.id.
captured_at | TIMESTAMPTZ | NOT NULL | Exact time of camera capture.
latitude | DECIMAL(9,6) | NOT NULL | GPS Latitude of detection point.
longitude | DECIMAL(9,6) | NOT NULL | GPS Longitude of detection point.
origin_city_inferred | VARCHAR(255) | - | System-calculated starting city.
dest_city_inferred | VARCHAR(255) | - | System-calculated destination city.
raw_image_url | TEXT | - | Link to the capture stored in cloud storage (S3).
Relationship Summary
Relationship Type | Source Table | Target Table | Foreign Key
One-to-Many | Carrier | Vehicle | vehicle.carrier_id
One-to-Many | Vehicle | Sighting | sighting.vehicle_id